## Task List
Week # | Task # | Task Description | Estimated Time (Hours)
8 | 1 | Reseach open ITS platforms | 2
8 | 2 | Identify existing (open source) SRS flashcard platform to fork | 2
8 | 3 | Fork SRS platform and set up dev environment (test functionality) | 4 | Total Hours | 100
8 | 4 | Figure out how to manually add flashcard data to the tool | 4
8 | 5 | Prepare and Submit Weekly Status Check | 0.5 | Week | Hours/week
9 | 6 | Manually add basic learning material to platform (3 categories: right and wrong answer pairs, and mnemonics/hints) - 30 pairs | 2 | 8 | 12.5
9 | 7 | Test software to ensure SRS functionality is working properly | 2 | 9 | 11.5
9 | 8 | Manually add two lessons worth of learning material to platform (3 categories: right and wrong answer pairs, and mnemonics/hints) - 100 pairs | 3 | 10 | 10.25
9 | 9 | Select ITS platform and document implementation plan | 4 | 11 | 11.75
9 | 10 | Prepare and Submit Weekly Status Check | 0.5 | 12 | 10.25
10 | 11 | Implement basic ITS (student, teaching, and domain models) | 6 | 13 | 11.25
10 | 12 | Create 3 dummy students for testing | 0.5 | 14 | 11.25
10 | 13 | Create training plans for students (student A should answer different questions correctly than student B) | 1.5 | 15 | 10.25
10 | 14 | Prepare and Submit Weekly Status Check | 0.25 | 16 | 11
10 | 15 | Prepare Milestone Progress Report with low-fidelity prototypes (drawn diagrams of user flows indicating working interactions) | 2
INTERMEDIATE MILESTONE 1 DUE
11 | 16 | Implement the students as users in the system | 1.5
11 | 17 | Test that student model is aligned with the student's successes/failures | 1
11 | 18 | ITS teaching model: problem solving suggestions - add a directed problem solving suggestion for each problem that the students get wrong | 2
11 | 19 | Implement the problem solving suggestions in the SRS system | 6
11 | 20 | Test that the software displays the correct problem solving suggestions | 1
11 | 21 | Prepare and Submit Weekly Status Check | 0.25
12 | 22 | Order learning material and add dependency information (to be used by ITS) | 2
12 | 23 | Implement the ITS teaching model: dependency-based teaching feature. Suggest/add new lessons based on proficiency with existing dependent lessons. | 6
12 | 24 | Test that the software does not add lessons untill proficiency in dependent lessons has been reached | 2
12 | 25 | Prepare and Submit Weekly Status Check | 0.25
13 | 26 | Improve usability of implemeneted ITS features (change console debug output into actual popups, redesign UI, etc) | 4
13 | 27 | Improve UI, add titles with App name, colors, etc | 2
13 | 28 | Test and resolve bugs | 2
13 | 29 | Prepare and Submit Weekly Status Check | 0.25
13 | 30 | Find classmates and friends to beta test application | 1
13 | 31 | Prepare Milestone Beta Application | 2
INTERMEDIATE MILESTONE 2 DUE
14 | 32 | Conduct beta tests | 2
14 | 33 | Review beta test results | 0.5
14 | 34 | Improve application usability, fix identified bugs, improve UI | 2.5
14 | 35 | Add additional learning data with associated problem solving suggestions and dependency information | 1
14 | 36 | Prepare and Submit Weekly Status Check | 0.25
14 | 37 | Work on Final Paper | 5
15 | 38 | Improve application usability, fix identified bugs, improve UI | 4
15 | 39 | Add additional learning data with associated problem solving suggestions and dependency information | 1
15 | 40 | Prepare and Submit Weekly Status Check | 0.25
15 | 41 | Work on Final Paper | 5
16 | 42 | Improve application usability, fix identified bugs, improve UI | 1
16 | 43 | Complete Final Paper | 2
16 | 44 | Develop Presentation Materials | 2
16 | 45 | Develop Presentation Script | 2
16 | 46 | Record Presentation | 2
16 | 47 | Edit Presentation | 2
FINAL PROJECT DUE